## SCHC Calendar
Task | Primary | Other 1 | Other 2 | Timeframe | 2017 | 2018
Spring Meeting Timeline
Send "Hold the Date" e-mail blast for Spring Meeting including reminder on poster session | President | Administrator | Poster Chair | 30 days (1 month) after Fall meeting | 2016-10-24 | 2017-10-23
Election slate sent to President for BOD review | Nominating Chair | President | BOD Chair | 112 days (16 weeks) before Spring meeting | 2016-12-03 | 2017-12-30
Finalize PDC brochures Post program on website | Professional Development Chair | Program Chair | Administrator | 112 days (16 weeks) before Spring meeting | 2016-12-03 | 2017-12-30
Prepare materials for distribution: Cover letter Registration form link Agenda Poster session information Membership activities | Membership Chair Program Chair | Poster Chair | President Administrator | 112 days (16 weeks) before Spring meeting | 2016-12-03 | 2017-12-30
Send e-mail blast reminder Focus: Professional Development courses | President | Administrator | Professional Development Chair | 84 days (12 weeks) before Spring meeting | 2016-12-31 | 2018-01-27
Send e-mail blast reminder Focus: Poster Session Call for Abstracts | Poster Chair | Administrator | President | 70 days (10 weeks) before Spring meeting | 2017-01-14 | 2018-02-10
Prepare postcard for mailing | Administrator | President |  | 56 days (8 weeks) before Spring meeting | 2017-01-28 | 2018-02-20
Send e-mail blast reminder Focus: Plenary speakers | President | Administrator | Program Chair | 56 days (8 weeks) before Spring meeting | 2017-01-28 | 2018-02-24
Send Press Release | Outreach Chair | Administrator |  | 56 days (8 weeks) before Spring meeting | 2017-01-28 | 2018-02-24
Send Election Ballot | Nominating Chair | Adminstrator | President | 56 days (8 weeks) before Spring meeting | 2017-01-28 | 2018-02-24
Communicate PDC Headcounts for decision making on holding all courses | Professional Development Chair |  |  | 42 days (6 weeks) before Spring meeting | 2017-02-11 | 2018-03-10
Send Election Ballot reminder | Nominating Chair | Adminstrator | President | 42 days (6 weeks) before Spring meeting | 2017-02-11 | 2018-03-10
Decide whether to hold all Professional Development courses | Professional Development Chair | Board of Directors |  | 35 days (5 weeks) before Spring meeting | 2017-02-18 | 2018-03-17
Send AV requirements for plenary sessions and PD courses to Arrangements Chair | Program Chair | Professional Development Chair |  | 30 days before Spring meeting | 2017-02-23 | 2018-03-22
Prepare timeline for Fall Meeting Send to Administrator | President | Administrator |  | 28 days (4 weeks) before Spring meeting | 2017-02-25 | 2018-03-24
Send e-mail blast reminder Focus: Final Poster Session Call for Abstracts | Poster Chair | Administrator |  | 28 days (4 weeks) before Spring meeting | 2017-02-25 | 2018-03-24
Make tour and networking arrangements | Membership Chair | Administrator |  | 28 days (4 weeks) before Spring meeting | 2017-03-04 | 2018-03-31
Finalize Poster Session Arrangements | Poster Chair | Administrator |  | 21 days (3 weeks) before Spring meeting | 2017-03-04 | 2018-03-31
Submit final program agenda, speaker bios, and presentation handouts | Program Chair | Administrator |  | 21 days (3 weeks) before Spring meeting | 2017-03-04 | 2018-03-31
Submit professional development course materials | Professional Development Chair | Instructors | Administrator | 21 days (3 weeks) before Spring meeting | 2017-03-04 | 2018-03-31
Submit committee and officer reports | Committee Chairs Officers | Administrator |  | 21 days (3 weeks) before Spring meeting | 2017-03-04 | 2018-03-31
Send e-mail blast reminder Focus: Professional Development Courses | President | Administrator | Professional Development Chair | 21 days (3 weeks) before Spring meeting | 2017-03-04 | 2018-03-31
Send e-mail blast reminder Focus: Program | President | Administrator | Program Chair | 14 days (2 weeks) before Spring meeting | 2017-03-11 | 2018-04-07
Send e-mail blast reminder Focus: Networking Opportunities | President | Administrator | Membership Chair | 7 days (1 week) before Spring meeting | 2017-03-18 | 2018-04-14
Spring Meeting |  |  |  |  | 2017-03-25 | 2018-04-21
Fall Meeting Timeline
Send "Hold the Date" e-mail blast for Fall Meeting | President | Administrator |  | 30 days (1 month) after Spring Meeting | 2017-04-24 | 2018-05-21
Finalize PDC brochures Post program on website | Professional Development Chair | Program Chair | Administrator | 112 days (16 weeks) before Fall meeting | 2017-06-03 | 2018-06-02
Prepare materials for distribution: Cover letter Registration form link Agenda Exhibit information Membership activities | Membership Chair Program Chair | Exhibit Chair | President Administrator | 112 days (16 weeks) before Fall meeting | 2017-05-06 | 2018-05-05
Send e-mail blast reminder Focus: Professional Development courses | President | Administrator | Professional Development Chair | 84 days (12 weeks) before Fall meeting | 2017-07-01 | 2018-06-30
Send e-mail blast reminder Focus: Exhibit and Reception | Exhibit Chair | Administrator |  | 70 days (10 weeks) before Fall meeting | 2017-07-15 | 2018-07-14
Prepare postcard for mailing | Administrator | President |  | 56 days (8 weeks) before Fall meeting | 2017-07-29 | 2018-07-28
Send e-mail blast reminder Focus: Plenary speakers | President | Administrator | Program Chair | 56 days (8 weeks) before Fall meeting | 2017-07-29 | 2018-07-28
Send Press Release | Outreach Chair | Administrator |  | 56 days (8 weeks) before Fall meeting | 2017-07-29 | 2018-07-28
Communicate PDC Headcounts for decision making on holding all courses | Professional Development Chair |  |  | 42 days (6 weeks) before Fall meeting | 2017-08-12 | 2018-07-14
Decide whether to hold all Professional Development courses | Professional Development Chair | Board of Dircetors |  | 35 days (5 weeks) before Fall meeting | 2017-08-19 | 2018-08-18
Send AV requirements for plenary sessions and PD courses to Arrangements Chair | Program Chair | Professional Development Chair |  | 30 days before Fall meeting | 2017-08-24 | 2018-08-23
Prepare timeline for Fall Meeting Send to Administrator | President | Administrator |  | 28 days (4 weeks) before Fall meeting | 2017-08-26 | 2018-08-25
Send e-mail blast reminder Focus: TBD | Poster Committee | Administrator |  | 28 days (4 weeks) before Fall meeting | 2017-08-26 | 2018-08-25
Make tour and networking arrangements | Membership Chair | Administrator |  | 28 days (4 weeks) before Spring meeting | 2017-09-02 | 2018-09-01
Submit final program agenda, bios, and presentation handouts | Program Chair | Administrator |  | 21 days (3 weeks) before Fall meeting | 2017-09-02 | 2018-08-25
Submit professional development course materials | Professional Development Chair | Instructors | Administrator | 21 days (3 weeks) before Fall meeting | 2017-09-02 | 2018-08-25
Submit committee and officer reports | Committee Chairs Officers | Administrator |  | 21 days (3 weeks) before Fall meeting | 2017-09-02 | 2018-08-25
Send e-mail blast reminder Focus: Professional Development Courses | President | Administrator | Professional Development Chair | 21 days (3 weeks) before Fall meeting | 2017-09-02 | 2018-08-25
Send e-mail blast reminder Focus: Program | President | Administrator | Program Chair | 14 days before Fall meeting | 2017-09-09 | 2018-09-08
Review Nominating Committee membership and fill vacancies as needed | President | Nominating Chair |  | 14 days (2 weeks) before Fall meeting | 2017-09-09 | 2018-09-15
Send e-mail blast reminder Focus: Networking Opportunities | President | Administrator | Membership Chair | 7 days before Fall meeting | 2017-09-16 | 2018-09-15
Fall Meeting |  |  |  |  | 2017-09-23 | 2018-09-22
Membership Year End Timeline
[5 empty] | 2016 | 2017
Send membership reminder | Web Committee | Membership Chair | Administrator | 90 days before membership expiration | 2016-10-02 | 2017-10-02
Send membership reminder | Web Committee | Membership Chair | Administrator | 60 days before membership expiration | 2016-11-01 | 2017-11-01
Send membership reminder | Web Committee | Membership Chair | Administrator | 30 days before membership expiration | 2016-12-01 | 2017-12-01
Send membership reminder | Web Committee | Membership Chair | Administrator | 15 days before membership expiration | 2016-12-16 | 2017-12-16
Send membership reminder | Web Committee | Membership Chair | Administrator | 7 days before membership expiration | 2016-12-24 | 2017-12-24
Send membership reminder | Web Committee | Membership Chair | Administrator | December 31 of current year | 2016-12-31 | 2017-12-31
[5 empty] | 2016-12-31 | 2017-12-31