## 2019-2020
Task | Primary | Other 1 | Other 2 | Timeframe | 2019 | 2020
Spring Meeting Timeline
Send "Hold the Date" e-mail blast for Spring Meeting including reminder on poster session | President | Administrator | Poster Chair | 30 days (1 month) after Fall meeting | 2019-10-21 | 2020-10-19
Election slate sent to President for BOD review | Nominating Chair | President | BOD Chair | 112 days (16 weeks) before Spring meeting | 2018-11-24 | 2019-12-07
Finalize PDC brochures Post program on website | Professional Development Chair | Program Chair | Administrator | 112 days (16 weeks) before Spring meeting | 2018-11-24 | 2019-12-07
Prepare materials for distribution: Cover letter Registration form link Agenda Poster session information Membership activities | Membership Chair Program Chair | Poster Chair | President Administrator | 112 days (16 weeks) before Spring meeting | 2018-11-24 | 2019-12-07
Send e-mail blast reminder Focus: Hotel Arrangements | Arrangements Chair | Administrator | President | 98 days (14 weeks) before Spring meeting | 2018-12-08 | 2019-12-21
Send e-mail blast reminder Focus: Poster Session Call for Abstracts | Poster Chair | Administrator |  | 70 days (10 weeks) before Spring meeting | 2019-01-05 | 2020-01-18
Send e-mail blast reminder Focus: Professional Development courses | Professional Development Chair | Administrator | President | 63 days (9 weeks) before Spring meeting | 2019-01-12 | 2020-01-25
Prepare postcard for mailing | Administrator | President |  | 56 days (8 weeks) before Spring meeting | 2019-01-19 | 2020-02-01
Send e-mail blast reminder Focus: Plenary speakers | Program Chair | Administrator | President | 56 days (8 weeks) before Spring meeting | 2019-01-19 | 2020-02-01
Send Press Release | Outreach Chair | Administrator |  | 56 days (8 weeks) before Spring meeting | 2019-01-19 | 2020-02-01
Send Election Ballot | Nominating Chair | Administrator | President | 56 days (8 weeks) before Spring meeting | 2019-01-19 | 2020-02-01
Send e-mail blast reminder Focus: Forum Sessions | Forum Chair | Administrator | President | 49 days (7 weeks) before Spring meeting | 2019-01-26 | 2020-02-08
Send e-mail blast reminder Focus: Professional Development courses | Professional Development Chair | Administrator | President | 42 days (6 weeks) before Spring meeting | 2019-02-02 | 2020-02-15
Communicate PDC Headcounts for decision making on holding all courses | Professional Development Chair |  |  | 42 days (6 weeks) before Spring meeting | 2019-02-02 | 2020-02-15
Send Election Ballot reminder | Nominating Chair | Administrator | President | 42 days (6 weeks) before Spring meeting | 2019-02-02 | 2020-02-15
Decide whether to hold all Professional Development courses | Professional Development Chair | Board of Directors |  | 35 days (5 weeks) before Spring meeting | 2019-02-09 | 2020-02-22
Send e-mail blast reminder Focus: Final Poster Session Call for Abstracts | Poster Chair | Administrator | President | 35 days (5 weeks) before Spring meeting | 2019-02-09 | 2020-02-22
Make tour and networking arrangements | Membership Chair | Administrator |  | 35 days (5 weeks) before Spring meeting | 2019-02-09 | 2020-02-22
Send AV requirements for plenary sessions and PD courses to Arrangements Chair | Program Chair | Professional Development Chair |  | 30 days before Spring meeting | 2019-02-14 | 2020-02-27
Prepare timeline for Fall Meeting Send to Administrator | President | Administrator |  | 28 days (4 weeks) before Spring meeting | 2019-02-16 | 2020-02-29
Send e-mail blast reminder Focus: Networking, Membership Dinners and Location Opportunities | Membership Chair | Administrator | President | 28 days (4 weeks) before Spring meeting | 2019-02-16 | 2020-02-29
Finalize Poster Session Arrangements | Poster Chair | Administrator |  | 21 days (3 weeks) before Spring meeting | 2019-02-23 | 2020-03-07
Submit final program agenda, speaker bios, and presentation handouts | Program Chair | Administrator |  | 21 days (3 weeks) before Spring meeting | 2019-02-23 | 2020-03-07
Submit professional development course materials | Professional Development Chair | Instructors | Administrator | 21 days (3 weeks) before Spring meeting | 2019-02-23 | 2020-03-07
Submit committee and officer reports | Committee Chairs Officers | Administrator | President | 21 days (3 weeks) before Spring meeting | 2019-02-23 | 2020-03-07
Send e-mail blast reminder Focus: Mobile App | Mobile Coordinator | Administrator |  | 21 days (3 weeks) before Spring meeting | 2019-02-23 | 2020-03-07
Send e-mail blast reminder Focus: Plenary speakers and Forum sessions | Program Chair Forum Chair | Administrator | President | 14 days (2 weeks) before Spring meeting | 2019-03-02 | 2020-03-14
Send e-mail blast reminder Focus: Networking Opportunities, Social Media, Awards, Mobile | Membership Chair, Social Media Chair, Mobile Coord | Administrator | President | 7 days (1 week) before Spring meeting | 2019-03-09 | 2020-03-21
Spring Meeting Dates |  |  |  |  | 2019-03-16 | 2020-03-28
Fall Meeting Timeline
Send "Hold the Date" e-mail blast for Fall Meeting | President | Administrator |  | 30 days (1 month) after Spring Meeting | 2019-04-15 | 2020-04-27
Finalize PDC brochures Post program on website | Professional Development Chair | Program Chair | Administrator | 112 days (16 weeks) before Fall meeting | 2019-06-01 | 2020-05-30
Prepare materials for distribution: Cover letter Registration form link Agenda Poster session information Membership activities | Membership Chair Program Chair | Poster Chair | President Administrator | 112 days (16 weeks) before Fall meeting | 2019-06-01 | 2020-05-30
Send e-mail blast reminder Focus: Hotel Arrangements | Arrangements Chair | Administrator | President | 98 days (14 weeks) before Fall meeting | 2019-06-15 | 2020-06-13
Send e-mail blast reminder Focus: Exhibit and Reception | Exhibit Chair | Administrator | President | 70 days (10 weeks) before Fall meeting | 2019-07-13 | 2020-07-11
Send e-mail blast reminder Focus: Professional Development courses | Professional Development Chair | Administrator | President | 63 days (9 weeks) before Fall meeting | 2019-07-20 | 2020-07-18
Prepare postcard for mailing | Administrator | President |  | 56 days (8 weeks) before Fall meeting | 2019-07-27 | 2020-07-25
Send e-mail blast reminder Focus: Plenary speakers | Program Chair | Administrator | President | 56 days (8 weeks) before Fall meeting | 2019-07-27 | 2020-07-25
Send Press Release | Outreach Chair | Administrator |  | 56 days (8 weeks) before Fall meeting | 2019-07-27 | 2020-07-25
Send e-mail blast reminder Focus: Webstreaming Option (if available) | Webstreaming Chair | Administrator | President | 49 days (7 weeks) before Fall meeting | 2019-08-03 | 2020-08-01
Send e-mail blast reminder Focus: Professional Development courses | Professional Development Chair | Administrator | President | 42 days (6 weeks) before Fall meeting | 2019-08-10 | 2020-08-08
Communicate PDC Headcounts for decision making on holding all courses | Professional Development Chair |  |  | 42 days (6 weeks) before Fall meeting | 2019-08-10 | 2020-08-08
Decide whether to hold all Professional Development courses | Professional Development Chair | Board of Directors |  | 35 days (5 weeks) before Fall meeting | 2019-08-17 | 2020-08-08
Send e-mail blast reminder Focus: Exhibit and Reception | Exhibit Chair | Administrator | President | 35 days (5 weeks) before Fall meeting | 2019-08-17 | 2020-08-15
Make tour and networking arrangements | Membership Chair | Administrator |  | 35 days (5 weeks) before Fall meeting | 2019-08-17 | 2020-08-15
Send AV requirements for plenary sessions and PD courses to Arrangements Chair | Program Chair | Professional Development Chair |  | 30 days before Fall meeting | 2019-08-22 | 2020-08-20
Prepare timeline for Fall Meeting Send to Administrator | President | Administrator |  | 28 days (4 weeks) before Fall meeting | 2019-08-24 | 2020-08-22
Send e-mail blast reminder Focus: Networking, Membership Dinners and D.C. Opportunities | Membership Chair | Administrator | President | 28 days (4 weeks) before Fall meeting | 2019-08-24 | 2020-08-22
Finalize Exhibit Arrangements | Exhibit Chair | Administrator | Arrangements Chair | 28 days (4 weeks) before Fall meeting | 2019-08-24 | 2020-08-22
Submit final program agenda, bios, and presentation handouts | Program Chair | Administrator |  | 21 days (3 weeks) before Fall meeting | 2019-08-31 | 2020-08-29
Submit professional development course materials | Professional Development Chair | Instructors | Administrator | 21 days (3 weeks) before Fall meeting | 2019-08-31 | 2020-08-29
Submit committee and officer reports | Committee Chairs Officers | Administrator |  | 21 days (3 weeks) before Fall meeting | 2019-08-31 | 2020-08-29
Send e-mail blast reminder Focus: Mobile App | Mobile Coordinator | Administrator |  | 21 days (3 weeks) before Fall meeting | 2019-08-31 | 2020-08-29
Send e-mail blast reminder Focus: Program and Webstreaming | Program Chair Webstreaming Chair | Administrator | President | 14 days (2 weeks) before Fall meeting | 2019-09-07 | 2020-09-05
Review Nominating Committee membership and fill vacancies as needed | President | Nominating Chair |  | 14 days (2 weeks) before Fall meeting | 2019-09-07 | 2020-09-05
Send e-mail blast reminder Focus: Networking Opportunities, Social Media, Awards, Mobile | Membership Chair, Social Media Chair, Mobile Coord | Administrator | President | 7 days before Fall meeting | 2019-09-14 | 2020-09-12
Fall Meeting Dates |  |  |  |  | 2019-09-21 | 2020-09-19
Membership Year End Timeline
[5 empty] | 2019 | 2020
Send membership reminder | Web Committee | Membership Chair | Administrator | 90 days before membership expiration | 2019-10-02 | 2020-10-02
Send membership reminder | Web Committee | Membership Chair | Administrator | 60 days before membership expiration | 2019-11-01 | 2020-11-01
Send membership reminder | Web Committee | Membership Chair | Administrator | 30 days before membership expiration | 2019-12-01 | 2020-12-01
Send membership reminder | Web Committee | Membership Chair | Administrator | 15 days before membership expiration | 2019-12-16 | 2020-12-16
Send membership reminder | Web Committee | Membership Chair | Administrator | 7 days before membership expiration | 2019-12-24 | 2020-12-24
Send membership reminder | Web Committee | Membership Chair | Administrator | December 31 of current year | 2019-12-31 | 2020-12-31
[5 empty] | 2019-12-31 | 2020-12-31