## Timeline-2023
Task | Primary | Other 1 | Other 2 | Timeframe | 2023
Membership Year End Timeline
Send membership renewals | Member Engagement | Membership | Administrator | 90 days before membership expiration | 2022-10-02 |  | We base the renewal on what is going on year end. We have an initial email and then two reminders that go out before 12/31. We have at least one reminder that their dues have lapsed that goes out early January. We can schedule whatever we want.
Send membership reminder | Member Engagement | Membership | Administrator | 60 days before membership expiration | 2022-11-01
Send membership reminder | Member Engagement | Membership | Administrator | 30 days before membership expiration | 2022-12-01
Send membership reminder | Member Engagement | Membership | Administrator | 15 days before membership expiration | 2022-12-16
Send membership reminder | Member Engagement | Membership | Administrator | 7 days before membership expiration | 2022-12-24
Send membership reminder | Member Engagement | Membership | Administrator | December 31 of current year | 2022-12-31
Dues Expiration |  |  |  |  | 2022-12-31
Spring 2023 Events
Election slate sent to President for BOD review | Nominating | President | BOD Chair | Dec. Board Meeting (12/15/22) | 2022-12-12 | hard date | Term begins April 1; Board to see slate at December Board meeting; Obtain bios/photos in Jan; send ballot in Feb; tabulate results in March and announce results to Board at March meeting and post results in March newsletter
Send Election Ballot | Nominating | Administrator | President | Approx. 8 weeks before April 1 Term | 2023-02-01 | hard date
Send Election Ballot reminder | Nominating | Administrator | President | two reminders
Prepare timeline for Annual Meeting Send to Administrator | President | Administrator |  |  |  |  | We should prepare and give to Board/Chairs at April board meeting
Term Start: | [5 empty] | 2023-04-01
Annual Meeting Timeline
Send "Hold the Date" e-mail blast for Annual Meeting | President | Administrator |  | Following April Biannual Board meeting with Committee Chairs | 2023-04-20 | hard date
Finalize PDC brochures Post program on website | Professional Development | Program | Administrator | 112 days (16 weeks) before meeting | 2023-06-10
Finalize Awards to be presented | Professional Development | Member Engagement | Administrator | 112 days (10 weeks) before meeting | 2023-07-22
Prepare materials for distribution: Registration form link Agenda Poster session information Membership activities | Member Engagement / Program | Poster | President Administrator | 112 days (16 weeks) before meeting | 2023-06-10
Send e-mail blast reminder Focus: Hotel Arrangements | Arrangements | Administrator | President | 98 days (14 weeks) before meeting | 2023-06-24
Send e-mail blast reminder Focus: Exhibit/Poster/Reception | Exhibit / Poster | Administrator | President | 70 days (10 weeks) before meeting | 2023-07-22 |  | Break into two? One for Exhibits and one for posters?
Send e-mail blast reminder Focus: Professional Development courses | Professional Development | Administrator | President | 63 days (9 weeks) before meeting | 2023-07-29
Prepare postcard for mailing | Administrator | President |  | 56 days (8 weeks) before meeting | 2023-08-05
Send e-mail blast reminder Focus: Early Bird Registration Deadline (8/4 (8 weeks before mtg)) | Program | Administrator | President | 7 days (1 week) before early bird reg | 2023-07-28 | HARD DATE
Send e-mail blast reminder Focus: Plenary speakers | Program | Administrator | President | 56 days (8 weeks) before meeting | 2023-08-05
Send Press Release | Member Engagement | Administrator |  | 56 days (8 weeks) before meeting | 2023-08-05
Send e-mail blast reminder Focus: Webstreaming Option (if available) | Webstreaming Coordinator | Administrator | President | 49 days (7 weeks) before meeting | 2023-08-12
Send e-mail blast reminder Focus: Professional Development courses | Professional Development | Administrator | President | 42 days (6 weeks) before meeting | 2023-08-19
Communicate PDC Headcounts for decision making on holding all courses | Professional Development |  |  | 42 days (6 weeks) before meeting | 2023-08-19
Decide whether to hold all Professional Development courses | Professional Development | Board of Directors |  | 35 days (5 weeks) before meeting | 2023-08-19
Send e-mail blast reminder Focus: Exhibit and Reception | Exhibit | Administrator | President | 35 days (5 weeks) before meeting | 2023-08-26
Finalize tour and networking arrangements | Member Engagement | Administrator |  | 35 days (5 weeks) before meeting | 2023-08-26
Send AV requirements for plenary sessions and PD courses to Arrangements | Program | Professional Development |  | 30 days before meeting | 2023-08-31
Prepare timeline for Fall Meeting Send to Administrator | President | Administrator |  | 28 days (4 weeks) before meeting | 2023-09-02
Send e-mail blast reminder Focus: Networking, Membership Dinners and D.C. Opportunities | Member Engagement | Administrator | President | 28 days (4 weeks) before meeting | 2023-09-02
Finalize Exhibit Arrangements | Exhibit | Administrator | Arrangements | 28 days (4 weeks) before meeting | 2023-09-02
Submit final program agenda, bios, and presentation handouts | Program | Administrator |  | 28 days (4 weeks) before meeting | 2023-09-02
Submit professional development course materials | Professional Development | Directors/Instructors | Administrator | 21 days (3 weeks) before meeting | 2023-09-09
Submit committee and officer reports | Committee Chairs Officers | Administrator |  | 21 days (3 weeks) before meeting | 2023-09-09
Send e-mail blast reminder Focus: Mobile App | Mtg App Coordinator | Administrator |  | 21 days (3 weeks) before meeting | 2023-09-09
Send e-mail blast reminder Focus: Program and Webstreaming | Program, Webstreaming Coordinator | Administrator | President | 14 days (2 weeks) before meeting | 2023-09-16
Review Nominating Committee membership and fill vacancies as needed | President | Nominating |  | 14 days (2 weeks) before meeting | 2023-09-16
Send e-mail blast reminder Focus: Networking Opportunities, Social Media, Awards, Mobile | Member Engagement | Social Media, Mtg App Coordinator | President Administrator | 7 days before meeting | 2023-09-23
Send e-mail blast reminder Focus - hotel registration deadline is 6p 9/8 |  |  |  |  | 2023-09-01 | HARD DATE - one week prior to hotel reg deadline
HOTEL REGISTRATION CUT-OFF DATE - set by hotel |  |  |  |  | 2023-09-08 | HARD DATE set by Hotel
2023 Meeting Dates |  |  |  |  | 2023-09-30 | 2023-10-05